## Test plan
Test Plan for VWO.com Login Page
1. Introduction
1.1 Purpose
This document provides a detailed test strategy for the VWO.com login page, ensuring it meets functional, security, usability, performance, and accessibility standards before production release.
1.2 Scope
In-Scope:
Login functionality (email, password, SSO)
Error handling & validation
Security mechanisms (password hashing, rate limiting)
UI responsiveness & cross-browser compatibility
Accessibility compliance (WCAG 2.1)
Out-of-Scope:
Post-login dashboard functionality
Third-party integrations (unless related to login)
2. Test Objectives
Category | Objective
Functional | Verify correct login, error messages, and redirections
Security | Prevent unauthorized access, SQLi, XSS, brute-force attacks
UI/UX | Ensure consistent design, responsive layout, and intuitive flow
Performance | Validate page load time (<2s) and API response efficiency
Compatibility | Cross-browser (Chrome, Firefox, Safari, Edge) & cross-device (iOS, Android) support
Accessibility | Screen reader support, keyboard navigation, color contrast
UI/UX Testing
Layout: Check alignment, spacing, font consistency.
Responsiveness: Test on mobile (iPhone/Android), tablet, desktop.
Error States: Ensure error messages are clear and non-disruptive.
Labels & Placeholders: Validate field hints (e.g., "Enter your email").
3.4 Performance Testing
Load Time: Login page should load in <2s (Lighthouse).
Stress Test: Simulate 500 concurrent users (JMeter).
API Check: /login endpoint response time <500ms.
3.5 Cross-Browser & Cross-Device Testing
Browsers:
Chrome (Latest)
Firefox (Latest)
Safari (Mac/iOS)
Edge (Latest)
Devices:
iPhone 14 (Safari)
Samsung Galaxy S23 (Chrome)
iPad (Safari)
Desktop (Windows/macOS)
3.6 Accessibility Testing
Screen Readers: NVDA, VoiceOver (iOS)
Keyboard Navigation: Tab/Enter/Esc functionality
Color Contrast: ≥ 4.5:1 (WCAG AA)
Alt Text: Verify for images (if any)
4. Test Environment
Component | Details
URL | https://staging.vwo.com/login
Test Data | Valid/Invalid credentials (masked in reports)
Tools | BrowserStack, Postman, JMeter, OWASP ZAP
OS | Windows 11, macOS Ventura, iOS 16, Android 13
5. Entry & Exit Criteria
5.1 Entry Criteria
✅ Build deployed to staging.
✅ Test cases reviewed & approved.
✅ Test data prepared.
5.2 Exit Criteria
✔️ 100% of P0/P1 test cases executed.
✔️ Zero critical (P0) defects open.
✔️ Performance benchmarks met.
6. Defect Reporting
Tool: JIRA
Fields:
Title: [P0/P1/P2] Brief issue description
Steps: Exact steps to reproduce
Expected vs. Actual: Screenshot/video
Environment: Browser/OS/Device
7. Risks & Mitigation
Risk | Impact | Mitigation
Browser-specific bugs | High | Test early on BrowserStack
Performance lag under load | Medium | Optimize API calls & CDN
Security vulnerabilities | Critical | Penetration testing pre-release

## Test Strategy
Test Strategy for VWO.com Login Page
1. Overview
This document defines the high-level testing approach for the VWO.com login page, ensuring it meets functional, security, usability, and performance requirements.
1.1 Goals
Validate end-to-end login functionality (email/password, SSO).
Ensure security compliance (OWASP Top 10).
Optimize performance (fast load times, low latency).
Guarantee cross-browser & mobile compatibility.
Verify accessibility (WCAG 2.1 AA).
1.2 Scope
In-Scope:
✅ Email/password login
✅ "Forgot Password" flow
✅ "Remember Me" functionality
✅ SSO (Google, Microsoft, etc.)
✅ Error handling & validation
Out-of-Scope:
❌ Post-login dashboard features
❌ Third-party integrations (unless login-related)
2. Testing Types & Approach
2.1 Functional Testing
Objective: Verify login workflows & error handling.
Techniques:
Positive Testing: Valid credentials → Successful login.
Negative Testing: Invalid credentials → Proper error messages.
Boundary Testing: Long emails/passwords, special characters.
State-Based Testing: "Remember Me" session persistence.
Tools:
Manual testing (exploratory + test cases)
Automation: Selenium/Cypress (for regression)
2.2 Security Testing
Objective: Prevent breaches & data leaks.
Tests:
✔ SQL Injection: ' OR '1'='1 → Blocked
✔ XSS: <script>alert(1)</script> → Sanitized
✔ Brute-Force Protection: Account lockout after 5 attempts
✔ HTTPS Enforcement: No mixed content
✔ Password Hashing: Verify bcrypt/scrypt
Tools:
OWASP ZAP / Burp Suite
Manual penetration testing
2.3 UI/UX Testing
Objective: Ensure intuitive, responsive design.
Checks:
Consistency: Fonts, colors, spacing (Figma vs. live).
Responsiveness: Mobile (iOS/Android), tablet, desktop.
Error States: Clear, non-technical error messages.
Labels & Placeholders: "Enter email" vs. "Email Address".
Tools:
BrowserStack / LambdaTest
Chrome DevTools (mobile emulation)
2.4 Performance Testing
Objective: Optimize speed & scalability.
Metrics:
Page Load: <2 seconds (Lighthouse)
API Response: /login <500ms
Concurrent Users: 1000+ logins/minute (peak load)
Tools:
JMeter / k6
Google Lighthouse
2.5 Cross-Browser & Cross-Device Testing
Objective: Consistent experience across platforms.
Coverage:
Browser | OS | Device
Chrome 120+ | Windows 11 | Desktop
Safari 16+ | macOS Ventura | MacBook
Firefox 115+ | Android 13 | Samsung S23
Edge 110+ | iOS 16 | iPhone 14
Tools:
BrowserStack / Sauce Labs
2.6 Accessibility Testing
Objective: WCAG 2.1 AA compliance.
Checks:
✔ Screen Readers: NVDA, VoiceOver
✔ Keyboard Navigation: Tab/Enter/Esc
✔ Color Contrast: ≥ 4.5:1 (e.g., error messages)
✔ Alt Text: For logos/icons
Tools:
Axe DevTools
WAVE Evaluation Tool
3. Test Automation Strategy
Scope:
Regression Suite: Login + error flows (50+ test cases).
CI/CD Integration: Run on every staging deploy.
Framework:
Web: Cypress (JavaScript)
API: Postman + Newman
Performance: k6 (scripted scenarios)
Maintenance:
Weekly script reviews
Dynamic selectors (not XPath-dependent)
4. Entry & Exit Criteria
4.1 Entry Criteria
✅ Staging environment ready.
✅ Test cases peer-reviewed.
✅ Test data (credentials, SSO config) prepared.
4.2 Exit Criteria
✔️ 100% P0/P1 test cases executed.
✔️ Zero critical defects open.
✔️ Performance SLA met (<2s load time).
5. Risk Management
Risk | Likelihood | Impact | Mitigation
Browser-specific CSS bugs | Medium | High | Test early on BrowserStack
SSO provider downtime | Low | Critical | Mock SSO in test env
API latency under load | High | Medium | Optimize DB queries
6. Deliverables
Test Cases (Excel/TestRail)
Defect Reports (JIRA)
Performance Benchmarks (Lighthouse/JMeter)
Accessibility Audit (Axe/WAVE)
7. Roles & Responsibilities
Role | Responsibility
QA Lead | Test planning, sign-off
QA Engineers | Execution, defect logging
Dev Team | Fixing critical bugs
DevOps | CI/CD pipeline setup

## Test cases
Scenario TID | Test Scenario | Test Case Id | Test Data | Test Case Title | Pre Condition | Steps to Execute | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
1 | VWO.com login page | 1 | Email: testuser@vwo.com Password: Secure@123 | Verify that the Login should work with the Valid User and password. | vwo.com page is loaded | 1. Enter registered email (e.g., user@vwo.com) 2. Enter correct password 3. Click "Log In" | User is redirected to dashboard | User is redirected to dashboard | Pass | Swati | NA | High | No
1 | VWO.com login page | 2 |  | Verify error on empty email and password | vwo.com page is loaded | 1. Leave both email and password fields empty | Error messages: “Email is required”, “Password is required” | Error messages: “Email is required”, “Password is required” | Pass | Swati | NA | High | No
1 | VWO.com login page | 3 | userexample.com / user@invalid | Invalid email format | vwo.com page is loaded | Enter incorrect email format (e.g. user.com), valid password | Show “Invalid email format” message | Show “Invalid email format” message | Pass | Swati | NA | Medium | No
1 | VWO.com login page | 4 | WrongPass123 | Incorrect password | vwo.com page is loaded | Enter valid email, wrong password | Error: “Incorrect email or password” | Error: “Incorrect email or password” | Pass | Swati | NA | High | No
1 | VWO.com login page | 5 | testuser123@vwo.com | Unregistered email | vwo.com page is loaded | Enter unknown email and valid password | Error: “Account does not exist” | Error: “Account does not exist” | Pass | Swati | NA | Medium | No
1 | VWO.com login page | 6 | Email: testuser@vwo.com Password: Secure@123 | Cross-browser login | vwo.com page is loaded | Test login on Chrome, Firefox, Edge, Safari | Login works consistently | Login works consistently | Pass | Swati | NA | Medium | No
1 | VWO.com login page | 7 | Correct Email: testuser@vwo.com Password: Secure@123 Correct Email: testuser111@vwo.com Password: Incorrect@123 | Error message disappears after correction | vwo.com page is loaded | Trigger error with invalid input, then correct and login | Error message clears after success | Error message clears after success | Pass | Swati | NA | Low | No
1 | VWO.com login page | 8 | Email: testuser@vwo.com Password: Secure@123 | “Remember Me” checkbox | vwo.com page is loaded | Enable checkbox, login, close browser, reopen | Email remains filled or session stays logged in | Email remains filled or session stays logged in | Pass | Swati | NA | Low | No
1 | VWO.com login page | 9 | Email: testuser@vwo.com Password: Secure@123 | Mobile responsiveness | vwo.com page is loaded | Open login on phone/tablet | Layout adjusts correctly; all controls accessible | Layout adjusts correctly; all controls accessible | Pass | Swati | NA | Medium | No